## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate (hours) | week 1 | week 2 | week 3 | week 4 | week 5 | Sprint Review
User Story #4 | 24 | Komal | In Progress | 35
Task11: Create a sign-up form |  |  | Complete | 10 | 10 | 3 | 0 | 0 | 0 | 0
Task12: store user details in members table |  |  | Complete | 15 | 15 | 5 | 5 | 0 | 1 | 0
Task13: Create Member's account |  |  | In Progress | 10 | 3 | 2 | 3 | 0 | 0 | 0
User Story #5 | 16 | Komal | In Progress | 20
Task14: Perfrom User Authentication |  |  | Complete | 8 | 5 | 0.5 | 0.5 | 0 | 0 | 2
Task15: Navigate to member’s profile |  |  | Complete | 10 | 3 | 5 | 1 | 1 | 1 | 0
Task16: load Member's updated profile |  |  | In Progress | 5 | 8 | 5 | 0 | 1 | 0 | 1
User Story #6 | 16 | Komal | In Progress | 20
Task17: Create Image table |  |  | In Progress | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task9: Allow camera access or file browsing |  |  | In Progress | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task10: Store Images at shared location |  |  | Not Started | 10 | 5 | 0.5 | 3 | 1 | 1 | 0
Total |  |  |  | 154 | 56 | 24 | 15.5 | 6 | 3 | 3